# Project prioritization worksheet

## Project Prioritization Criteria

| Criteria | ### Description | Relative Criteria Weighting | Project Scoring Scale |
| --- | --- | --- | --- |
| 1 | Clearly-defined Stakeholder Group | Heavy | Strong to Weak |
| 2 | Alignment with current corporate strategy | Variable | Excellent to Poor |
| 3 | Return on Investment | Heavy | Clear to Ambiguous |
| 4 | Clearly-defined Project Goals | Critical | Yes / No |
| 5 | Alignment with organizational capability | Light | Strong to Weak |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |

# Project prioritization worksheet, 
continued

## Project Prioritization Worksheet

| Criteria | Weighting | Project 1 | Project 2 | Project 3 | Project 4 | Project 5 | Project 6 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Heavy | Very Strong | Medium | Medium | Strong | Medium | Strong |
| 2 | Variable | Good | Unknown | Low | Excellent | Unknown | Excellent |
| 3 | Heavy | Clear | Clear | Ambiguous | Clear | Clear | Clear |
| 4 | Critical | Yes | No | Yes | Yes | Yes | Yes |
| 5 | Light | Medium | Strong | Strong | Very Strong | Weak | Very Strong |
| 6 |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |
| Score |  | Very High | Low | Medium | High | Medium | High |
| Rank |  | 1 | Not Ranked | 5 | 2 | 4 | 3 |

# Project selection worksheet

## Organizational Forecaster

The project priority list helps determine when projects can be scheduled to begin and takes into account both the priority of the project and the capacity of the organization.

Here is an example the prioritized projects might be scheduled.  Note how project six ends up being scheduled to start earlier than higher priorities because the organization’s capacity permits it.

| TimeScale | Q3/2003 | Q4/2003 | Q1/2004 | Q2/2004 | Q3/2004 | Q4./2004 | Q1/2005 | Q2/2005 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Capacity | 39,750 h | 42,500 h | 43,250 h | 42,000 h | 41,000 h | 43,000 h | 42,500 h | 43,000 h |
| Forecasted Utilization | 39,500 h | 41,900 h | 39,500 h | 36,750 h | 34,000 h | 33,770 h | 32,000 h | 32,100 h |
| Project Code 1 |  | 385 h | 1325 h | 1250 h | 625 h | 705 h | 1000 h | 100 h |
| Project Code 2 |  |  |  |  |  |  |  |  |
| Project Code 3 |  |  |  |  | 1100 h | 1225 h | 1625 h | 975 h |
| Project Code 4 |  |  | 900 h | 1900 h | 2350 h | 3200 h | 2800 h |  |
| Project Code 5 |  |  |  |  | 900 h | 875 h | 625 h |  |
| Project Code 6 | 215 h | 385 h | 450 h | 1550 h | 875 h | 1600 h | 650 h |  |
| Updated Forecast | 39,715 h | 42,670 h | 42,175 h | 41,450 h | 39,850 h | 41,375 h | 38,700 h | 33,175 h |