| #### New Product Development Project (07-4392) Project Plan Company Confidential |  |  |  |  |
| --- | --- | --- | --- | --- |
| Author: | Project Management Team |  | Approved: | May 27, 2003 |
| Approved By |  |  |  |  |
| Director, Marketing |  | Robert Hayes |  |  |
| Director, Enterprise Project Management |  | Peter Lo |  |  |
| Director, Manufacturing Operations |  | Diane Williams |  |  |
| Manager, Product Development |  | Kamal Sankar |  |  |
| Director, Sales |  | Catherine Turner |  |  |
| Project Manager |  | Project Management Team |  |  |
| Version: | 1.1 |  | Revised: | June 2, 2003 |

Document Purpose

The purpose of this document is to develop and document the “HOW” of the project, establishing a baseline that reasonably predicts the project’s scope, time, and cost at completion. Its aim is to create a common understanding of how the project will achieve its goal and objectives.

Project Charter

Background

Innovative product development has been a hallmark of our company success for the last 15 years.  We have not only met consumer needs, but have also helped them uncover new ways of using our products and services to enhance their situation.  We have expanded the importance of the industry in the eyes of the consumer.

Our recent setbacks have hurt us, though.  We find ourselves struggling internally with employee motivation even as our customers become restless with our performance and service of late.  The senior management team has considered ways for the company to re-invent itself.  It has chosen a route which will allow us to re-connect with what we do best (meeting consumer needs through new products) using a development project that showcases what makes this company great (a talented, motivated staff).  The expectations for this project go well beyond the product that it introduces.

Goal

The project is a dramatic, successful launch our new product into the marketplace.  The organizational goal is to use the launch as a platform for overcoming the challenges of our company’s recent history.  We want to restore the confidence of loyal customers and create opportunities for new customer relationships.  Re-energizing staff throughout the company is integral to the project goal.  The quality and effectiveness of how this project is run is of prime importance.

Objectives

The objectives for this project are:

To make a sound determination whether it is feasible to bring our new product to market now.

To develop, trial, and introduce our new product to the wide market by September 16, 2004.

To run the project such that it serves as a source of motivation and pride for company staff.

Deliverables

Product Development Deliverables

Product Screening Stage Presentation

Investigation Stage Plan

Lab Scale Product

Investigation Stage Presentation

Development Stage Plan

Product Prototype

Customer Product Test Plan

Customer Evaluation Product

Manufacturing Design Document

Development Stage Presentation

Pilot Stage Plan

Initial Trial Production Batch

Main Trial Production Batch

Commercialization Plan

Pilot Stage Presentation

New Production Equipment

Production Trial Plan

Initial Commercial Product Batch

Product Launch Event

Commercialization Stage Report

Post-Commercialization Review Stage Report

Project Management Deliverables

Project Plan Document (with supporting schedule)

Weekly Status Reports

Project Closure Report

Product Quality Control Reports

Boundaries

Inclusions:

Recommendations will be made for additional product development beyond the completion of this project.

All work associated with market research and product development.

Legal and patent issues relating to the introduction of this product.

Product launch activities relating to manufacturing.

Exclusions:

Development of specific marketing and sales strategies and materials.

Constraints

The following constraints have been applied to this project:

The product must be launched by September 16, 2004.

The project must be managed exceptionally well to help motivate the company.

External Dependencies

Incoming External Dependencies

Receive marketing materials from Marketing department

Outgoing External Dependencies

Provide marketing research data to Marketing department

Triangle Flexibility

Time (Least Flexible)

Scope

Cost (Most Flexible)

Stakeholders

Key Stakeholders

| Name | Vested Interest |
| --- | --- |
| Robert Hayes | Sponsor (Marketing) |
| Peter Lo | Stakeholder (Project Management) |
| Diane Williams | Stakeholder (Manufacturing) |
| Kamal Sankar | Stakeholder (Product Development) |
| Catherine Turner | Stakeholder (Sales) |
| Project Management Team | Project Manager |
| Tom Morton | Team Member (Product Engineering) |
| Karen Salandu | Team Member (Product Engineering) |
| Margaret Johnson | Team Member (Legal) |
| Robert Brooks | Team Member (Marketing) |
| Alastair Telford | Team Member (Process Engineering) |
| Linda Jackson | Team Member (Manufacturing Engineering) |
| Gerald Hough | Team Member (Safety) |
| Charles Metcalfe | Team Member (Accounting) |
| William Rowley | Team Member (Purchasing) |

Other Stakeholders

| Name | Vested Interest |
| --- | --- |
| All Company Staff | Motivated and re-energized by this product development project. |
| Existing Customer Base | Restored loyalty through this new product introduction. |
| New Customer Opportunities | Expanded opportunities to reach a new customer base with this product. |

Project Implementation

Approach

Product Development Approach

This project will utilize our standard 5-stage product development method with the optional Post-Commercialization Review stage added.  The stages for this project will be:

Product Screening Stage

Investigation Stage

Development Stage

Pilot Stage

Commercialization Stage

Post-Commercialization Review Stage

Project Management Approach

This project will be managed using the company’s standard enterprise project management methodology.  In this methodology, individual project team members from various functional units report into the enterprise department for project related activities.  Normal functional reporting structures are maintained for all other work that individuals perform outside the scope of this project.  For further information on the methodology and its standards, visit the enterprise intranet site.

Roles & Responsibilities

This project will be run at an enterprise level.  It is expected to involve staff from most organizational units.

The project management team from the enterprise department will manage the project.  The roles and responsibilities listed below are defined as they relate to the management of this project, not to the organization as a whole.

Project Manager

Develop project plan and schedule that details the full scope of the project and includes solid time and cost estimates.

Negotiate and establish attainable scope, time, and cost baselines.

Maintain team members’ focus on project goals and objectives.

Facilitate and integrate the work of the project team in order to meet the expected scope, time, and cost of the project.

Communicate activity expectations to team members, monitor their progress, provide prompt feedback, and follow through with performance-based consequences.

Monitor critical path activities and ensure they get completed on time.

Maintain schedules in order to accurately reflect past performance and produce valid future projections.

Manage project scope, time, and cost in order to meet established success criteria.

Communicate project performance to upper management, project team members, and peers.

Manage the expectations of all stakeholders.

Initiate the change control process as required and adjust baselines when changes are approved.

Identify and document all risks, follow risk mitigation plans, identify risk symptoms, and execute contingency plans when risks occur.

Document, track, and ensure timely closure of issues and action items.

Ensure that the project’s goal and objectives are met.

Ensure that the desired quality is achieved for all project deliverables.

Evaluate the project actuals against their baselines, summarize approved changes and their impacts, analyze key project events, and identify lessons learned when projects are completed.

Project Sponsor and User Representative

Sign off on the project charter and plan when in agreement.

Manage any changes to the existing baselines by actively participating in the change control process as a member of the CCB.

Managers of project managers

Review Project charter, plan and schedule.

Help negotiate attainable scope, time, and cost baselines.

Ensure that required resources are available.

Support project managers by following through with performance-based consequences, using progress reviews, and the company's annual performance review.

Communicate project performance to upper-level management.

Help manage the expectations of all project stakeholders.

Help identify and manage project risks.

Help resolve issues.

Ensure that project goals and objectives are met.

Participate in project closure meeting.

Enforce all documented standards and guidelines.

Ensure that the project manager follows the defined project management methodology.

Team members

Work with the project manager to develop the Work Breakdown Structure (WBS).

Provide realistic estimates.

Work with project managers to identify activity dependencies.

Complete action items within the defined time frame.

Ensure that activities with little or no float are completed on time.

Help the project managers keep the resource calendar up to date.

Return time sheets in a timely fashion to ensure that each activity’s actuals and estimates to complete reflect current reality.

Communication

Expected communication interfaces within the project are detailed below.  The project management team using the project roles and responsibilities for guidance will evaluate unforeseen interfaces.

| What | Who |  | When | How |
| --- | --- | --- | --- | --- |
|  | From | To |  |  |
| Project Plan | Project manager | All stakeholders | At the end of planning, and after approved changes. | Printed document |
| Status Reports | Project manager | All stakeholders | Every Tuesday by 2:30 p.m. | E-mailed Adobe file |
| Project Team Update | Project manager | All project team members | Every Thursday (9:30 - 10:00) | Coordination meeting |
| Completed timesheets | All project team members | Project manager | Every Monday, start of business | Timekeeping software |

Change Control

The members of the change control board (CCB) are the Project Management Team, Robert Hayes, and Kamal Sankar.

Changes will be categorized as either:

Requested Modification
A project stakeholder requests a change that affects an approved version of the Project Plan (for example, the Goal, Objectives, Boundaries, Constraints, External Dependencies, certain Required Resources, and Key Milestones), System Requirements, or Design Specifications.

Corrective Action
Time and/or cost index thresholds exceed 10% between the scheduled and current baseline views.

To execute the change control process:

- Determine if the change is a formal change and reject it if it is not.

Document the change using a change request.

Solicit impacts from stakeholders using an impact request.

Summarize impacts and document the overall impact using the change request.

Present change request to the CCB for a decision.

Document the disposition using the change request.

Establish a new baseline if the change is approved.

Quality

The new product will be developed to satisfy industry standards for this product class.  The relevant standards for this product include:

International Association Standards 1999 – Section 3 and 7.

National Standards 1996 – Article 4.

Standards will be assessed during prototyping and initial manufacturing using our routine quality control measures.  The prototyping quality review will be used to guide the manufacturing design process.  Quality control measurements during initial manufacturing will occur on the Monday, Wednesday and Friday for the longer of 6 weeks, or until specifications are reached with 99.997% consistency over a 3 week period.

Evaluation of quality control results will be performed weekly by the entire project team.  If required, corrective actions to the manufacturing process to meet standards will be implemented after the each manufacturing review.

Required Resources

The following departments will need to be involved in project work.  Specific skills required are listed in parentheses:

Enterprise (Project Management)

Legal

Marketing (Research, Product Engineering)

Manufacturing (Process Engineering, Manufacturing Engineering, Safety)

Finance (Accounting, Purchasing)

Budget and contingency support for this project will come from the Marketing department.

Key Milestones

| Milestone | Date |
| --- | --- |
| Project Start | 02-Jun-03 |
| Product Screening Stage Complete | 15-Jul-03 |
| Investigation Stage Complete | 31-Jul-03 |
| Development Stage Complete | 14-Jan-04 |
| Pilot Stage Complete | 02-Jun-04 |
| Product Launch Complete | 13-Sep-04 |
| Commercialization Stage Complete | 23-Sep-04 |
| Post-Commercialization Review Stage Complete | 23-Jun-05 |
| Project Complete | 15-Jul-05 |

Success Criteria

| Component | Variance/Index |
| --- | --- |
| Scope | - 20 % |
| Time | + 0 % |
| Cost | +50 % |

Revisions

| Date | CR# | Description |
| --- | --- | --- |
| 02-Jun-03 | CR-001 | Revised planning effort with added objective. |