# assessing progress and status

Project Progress for Period Ending:		07-Jun-03

|  | Last Week |  | This Week |  |
| --- | --- | --- | --- | --- |
|  | Baseline | Actual | Baseline | Scheduled |
| Work (Hours) |  |  |  |  |
| #### Project Overhead | 26 h | 12 h | 26 h | 26 h |
| ### Project Activities | 44.4 h | 41 h | 62.97 h | 51.37 h |
| Total | 70.4 h | 53 h | 88.97 h | 77.37 h |
| Cost (Dollars) |  |  |  |  |
| #### Project Overhead | $ 3,190.00 | $ 1,525.00 | $ 3,190.00 | $ 3,190.00 |
| Project Activities | $ 5,448.00 | $ 5,045.00 | $ 7,491.20 | $6,034.20 |
| ##### Total | $ 8,638.00 | $ 6,570.00 | $ 10,681.20 | $ 9,224.20 |
| Scope (Number of Activities) |  |  |  |  |
| Started or to start | 6 | 7 | 2 | 1 |
| Worked on or planned to work on | 6 | 7 | 6 | 7 |
| Completed or to complete | 2 | 1 | 1 | 2 |

###### What is the status of the project?

|  | Early/Under () | On plan () | Late/Over () |
| --- | --- | --- | --- |
| ###### Time |  |  |  |
| Cost |  |  |  |
| Scope |  | ? |  |

What work is scheduled for the 2nd week (June 8 – 14)?

| ID | Name | Critical? (Yes/No) | To Complete This Week? | Planned Hours This Week |
| --- | --- | --- | --- | --- |
| 12 | ## Gather info for go / no go decision | No | Yes | 19 h |
| 13 | Prepare product screening stage presentation | No | No | 2.17 h |
| 18 | Develop investigation plan | Yes | Yes | 1 h |
| 19 | Evaluate the market | No | No | 4.2 h |
| 20 | Analyze the competition | No | No | 0 h |
| 22 | Produce the lab scale product | Yes | No | 25 h |

| ## How many activities appear under-estimated? | 1 |
| --- | --- |
| How many activities appear over-estimated? | 3 |

Is it relevant that Activity 22 started before Activity 18 finished? Why or why not?

The dependency between Activities 18 and 22 no longer seems correct. It may be that Activity 18 must finish before Activity 22 can finish, in which case the Finish-to-Start dependency could be replaced with a Finish-to-Finish relationship. Or, the dependency might be deleted altogether if the activities can be performed independent of one another.