# performance metrics — State Report (Week 2)

| Milestone Completion |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Current Baseline | Scheduled | Variance | Index | Status |
| Project Start | 2-Jun-03 |  |  |  |  |
| Product Screening Stage Complete | 2-Jul-03 | 11-Jul-03 | 9 d | 130% | Incomplete |
| Investigation Stage Complete | 31-Jul-03 | 8-Aug-03 | 8 d | 114% | Incomplete |
| Development Stage Complete | 14-Jan-04 | 22-Jan-04 | 8 d | 104% | Incomplete |
| Pilot Stage Complete | 2-Jun-04 | 10-Jun-04 | 8 d | 102% | Incomplete |
| Product Launch Stage Complete | 13-Sep-04 | 21-Sep-04 | 8 d | 102% | Incomplete |
| Commercialization Stage Complete | 23-Sep-04 | 1-Oct-04 | 8 d | 102% | Incomplete |
| Post-Commercialization Comp. | 23-Jun-05 | 1-Jul-05 | 8 d | 101% | Incomplete |
| Project Completion | 15-Jul-05 | 25-Jul-05 | 10 d | 101% | Incomplete |
| Estimate at Completion |  |  |  |  |  |
|  | Current Baseline | Scheduled | Variance | Index | Actuals |
| Cost | $649,864 | $648,989 | -$875 | 100% | $13,408 |
| Work | 5,345 h | 5,338 h | -7 h | 100% | 112 h |

# trend Report (Week 2)

|  | Variance |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Milestones | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Trend |
| Product Screening Stage Complete | 2 d | 9 d |  |  |  |  |  |
| Investigation Stage Complete | -1 d | 8 d |  |  |  |  |  |
| Development Stage Complete | -1 d | 8 d |  |  |  |  |  |
| Pilot Stage Complete | -1 d | 8 d |  |  |  |  |  |
| Product Launch Stage Complete | -3 d | 8 d |  |  |  |  |  |
| Commercialization Stage Complete | -1 d | 8 d |  |  |  |  |  |
| Post-Commercialization Comp. | -1 d | 8 d |  |  |  |  |  |
| Project Completion | -1 d | 10 d |  |  |  |  |  |
| Estimate at Completion (Cost) | -$1,860 | -$875 |  |  |  |  |  |
|  | Index |  |  |  |  |  |  |
| Estimate at Completion (Hours) | 100% | 100% |  |  |  |  |  |
| Spend Plan (Hours) | 75% | 70% |  |  |  |  |  |
| Performance to Estimate (Hours) | 133% | 82% |  |  |  |  |  |
| Number of Activities | 100% | 100% |  |  |  |  |  |